## Slide 1: Chapter 10 – Project Management

## Slide 2: Motivation
Engineers are regularly engaged in projects in their careers!
Middle management continues to shrink
Industry now organizes more around projects than functions.
Notes: Middle management is dying, industry continu

## Slide 3: Motivation, cont’d
Engineers have led the way on project management, it is now “hot and trendy”.
#1 Area of Continuing Education reported by Penn State Behrend ECE alumni.
Penn State Behrend School of Engineering Survey 2003 of Fortune 500 companies- #1 required skill for new engineers = PROJECT MANAGEMENT SKILLS

## Slide 4: The HOLY GRAIL!
To complete the project
  On-time
  Within budget
  So that it meets the requirements

## Slide 5: Learning Outcomes
By the end of this chapter, you should
Be able to create a work breakdown structure.
Be able to create network diagrams and Gantt charts.
Be able to determine the critical path for completing a project and the float time for each activity in the plan.
Be able to conduct break-even analysis and understand some basic methods of cost estimation.
APPLY THIS TO YOUR PROJECT – YOU MUST LEARN BY DOING!

## Slide 6: 10.1 Work Breakdown Structure
Work Breakdown Structure (WBS)
Activity

## Slide 7: WBS
Tasks
Deliverables

## Slide 8: WBS - Definition
From MIL-HDBK 881
A product-oriented family tree composed of hardware, software, services, data, and facilities. The family tree results from systems engineering efforts.
A WBS displays and defines the product, or products, to be developed and/or produced. It relates the elements of work to be accomplished to each other and to the end product.
A WBS can be expressed down to any level of interest. However the top three levels are as far as any program or contract need go unless … .

## Slide 9: Elements of the Project Plan
Activities
Responsibilities
Timeline
Dependencies
Costs
HINT: THESE THINGS OUGHT TO BE IN YOUR PLAN!

## Slide 10: Example – Thermometer Design
Problem: Create the WBS for a temperature monitoring system design

## Slide 11: Example – Thermometer, cont’d
There are three main tasks
The analog interface circuitry.
The LED & digital circuitry.
Integrate & Test.

## Slide 12: Example – Thermometer, cont’d
Activity: Design Circuitry
Description: Complete the detailed design and verify it.
Deliverables/Checkpoints: 1) Circuit schematic, and 2) Verify in simulation.
Duration: 14 days.
People: Jana (1), Rob (1)
Resources: PC, SPICE Simulator
Predecessors: none

## Slide 13: Example – Thermometer Design
ID | Activity | Description | Deliverables / Checkpoints | Duration (days) | People | Resources | Predecessors
1 | Interface Circuitry |  |  |  |  |  | 
1.1 | Design Circuitry | Complete the detailed design and verify it in simulation. |  Circuit schematic  Simulation verification | 14 | Rob (1) Jana (1) |  PC  SPICE simulator | 
1.2 | Purchase Components |  |  Identify parts  Place order  Receive parts | 10 | Rob |  | 1.1
1.3 | Construct & Test Circuits | Build and test. |  |  |  |  | 
1.3.1 | Current Driver Circuitry | Test of circuit with sensing device. |  Test data  Measurement of linearity | 2 | Jana (1) Rob (2) |  Test bench  Thermo- meter | 1.2
1.3.2 | Level Offset & Gain Circuitry | Test of circuit with voltage inputs. |  Test data  Measurement of linearity | 3 | Rob (1) Jana (2) |  Test bench | 1.2
1.3.3 | Integrate Components | Integrate the current driver and offset circuits. |  Test data verifying functionality and linearity requirement | 5 | Rob (1) Jana (1) |  Test bench  Thermo- meter | 1.3.1 1.3.2

## Slide 14: Activity Duration Estimates
PERT: Project Evaluation and Review Technique
Statistical methods to estimate project completion time.
Based on earlier studies that show that project task completion follows a Beta probability distribution.

## Slide 15: 10.2 Network Diagrams
A network diagram is a ???
We will use AON (Activity on Node)

## Slide 16: AON Basics

## Slide 17: Example: Network Diagram
Problem: identify the paths to completion.

## Slide 18: Network Diagram Definitions
Critical Path =
Slippage =
Float =

## Slide 19: Example 10.2
Problem: Calculate the float for all activities in network.

## Slide 20: 10.3 Gannt Charts

## Slide 21: 10.4 Cost Estimation
How do you complete projects within cost?
Need to be able to estimate costs for
  System design
  Development
  Manufacture
Basics presented here – complex problem that requires experience.

## Slide 22: Break-Even Analysis
Fixed costs
Variable Costs
Break-Even Point

## Slide 23: Break-Even Analysis

## Slide 24: Cost Models

## Slide 25: 10.6 Guidance
Take the initial time estimates for activities and double them!
Assign a lot of time for testing and integration.
Factor in lead times for part ordering.
Assign a project manager(s).
Do not assign all team members to all tasks.
Track the progress versus the plan.
Don’t become a slave to the plan.
Experience counts.

## Slide 26: 10.7 Project Application
A Project Plan should contain
Work Breakdown Structure. Identify the activities, deliverables, responsibilities, duration, resources, and dependencies.
Gantt Chart and/or Network Diagram. Provide a graphical representation of the project plan.
Costs. Develop a tabulated list of costs and for the equipment, materials, and labor necessary to carry out the project.

## Slide 27: 10.8 Summary
Three important objectives of project management are to complete the project
  On-time
  Within budget
  To meet the needs of the user.
WBS – hierarchical breakdown of activities needed to complete a project.
Network diagram – graphical representation of activities for project – can use for quantitative analysis of project.
Cost estimates
  Break-even analysis
  Cost estimation models